COCOUNSEL

Skill: Review Documents

Result created: 04/24/2026

Prompt:

- Review the declaration of John Longardo for inconsistencies and vulnerabilities.

Files:

- Condensed Super Combo Binder1.pdf

Result:

Result:

### Executive Summary

- Payment timeline and documents are internally inconsistent: The declaration relies on an AIA A101 contract “made” 9/2/2025, but the owner’s termination notice refers to an “unsigned proposal contract,” creating uncertainty about which governing agreement applies and what payment terms control the “earned and unpaid” analysis.

- “Overpaid/mobilization” conclusions are conclusory and potentially contradicted by JAT’s own AIA pay app: The pay application shows substantial “earned” work through 9/30/2025, including mobilization, demolition, and piles/shoring, supporting a current payment due, which cuts against the blanket assertion that JAT was fully paid or overpaid by the time of lien filing.

- No project-close accounting through the lien date: The declaration does not quantify “earned” work through 12/16/2025 (lien filing), even though the complaint alleges Marine continued through 12/4/2025, creating a gap on whether a lien fund existed on that date.

- Waiver of JAT’s claim does not extinguish owner’s pre-lien obligations: JAT’s unilateral “waiver” of claims is used to show no lien fund, but a contractor’s after-the-fact waiver cannot retroactively negate sums already earned and unpaid as of lien filing.

### Detailed Vulnerabilities

- Contract formation uncertainty undermines “no fund” premise

  - What the declaration states: JAT and owner entered an AIA A101-2017 as of 9/2/2025; owner terminated on 12/5/2025.

  - Why vulnerable: The owner’s termination letter concurrently describes an “unsigned proposal contract.” If the AIA was not fully executed, the governing terms for “earned” work, retainage, and progress payment triggers may differ, weakening any categorical assertion that advance/mobilization payments eliminated the lien fund.

  - Supporting details: The AIA shows a $3,460,474 contract with defined payment and retainage mechanics, including 10% retainage and architect certification, which would matter to what is “earned and unpaid.”

- “Overpaid based on mobilization” is asserted, not proven, and may conflict with JAT’s own AIA G702/G703

  - What the declaration states: A substantial portion of payments were mobilization billed in advance; after crediting actual value of work, JAT was fully paid and overpaid.

  - Why vulnerable: JAT’s AIA Application and Certificate for Payment No. 2 through the period ending 9/30/2025 shows:

    - Total completed/stored to date: $504,147.40

    - Retainage: $50,414.74

    - Total earned less retainage: $453,732.66

    - Less previous certificates: $277,290.00

    - Current payment due: $176,442.66 These are JAT’s own sworn payment metrics indicating “earned” value beyond the first $277,290 draw, undercutting the blanket “overpaid” conclusion unless JAT reconciles and subtracts later change events.

  - Concrete examples:

    - G703 continuation sheet allocates $346,047.40 to Mobilization at 100% complete, plus partial Demolition ($23,100) and Piles/Shoring ($135,000), evidencing earned progress consistent with the AIA framework.

- No line-by-line reconciliation from 10/1–12/4/2025

  - What the declaration states: JAT was terminated 12/5/2025; no money due from owner to JAT as of 12/16/2025; JAT waives present claims.

  - Why vulnerable: The record lacks a reconciliation from 10/1 to 12/4 work period (when Marine alleges last work) that nets:

    - Earned line items through 12/4,

    - Less retainage,

    - Less paid-to-date ($277,290 checks + $60,000 wire),

    - Less backcharges/offsets, to show a zero-or-negative balance as of 12/16. Without that, “no fund” is a conclusion, not an accounting.

  - Concrete gap: Marine’s invoices include a 9/25/2025 invoice for $121,500 mobilization/material deposit and a signed waiver “up to 9/30/25,” leaving October–December work unaddressed in the owner–contractor accounting.

- Reliance on contractor’s present-tense “waiver” is legally and factually fragile

  - What the declaration states: JAT waives any present claim; liens by Marine or Urban Industrial do not mean money is due.

  - Why vulnerable: Lien fund existence is determined as of the lien filing date based on sums “earned and unpaid” on the prime contract. A subsequent or contemporaneous “waiver” by the contractor does not by itself erase amounts already earned and unpaid as of 12/16/2025. The declaration does not show that, as of 12/16, there was truly no earned but unpaid balance under the contract terms.

  - Concrete detail: Urban Industrial also filed a lien for $109,300 for demolition, which at least corroborates that multiple subs claim unpaid downstream, increasing the burden to show the upstream owner–contractor balance was genuinely zero as of filing.

- Payment evidence is incomplete for a dispositive “no fund” finding

  - What the declaration includes: Two 9/4/2025 checks totaling $277,290 and a scheduled 11/3/2025 wire of $60,000; an AIA pay app through 9/30/2025.

  - Why vulnerable:

    - The 11/3 wire screenshot shows “Needs approval,” not proof of completion/receipt into JAT’s account; there is no bank confirmation or statement showing posting, which opens an evidentiary gap on the $60,000.

    - No owner/architect certificate of payment or proof of payment for the $176,442.66 “current payment due” per the 9/30 pay app is provided, leaving open whether that amount was ever paid, partially paid, or denied—critical to “earned and unpaid” as of December 16.

- Termination letter characterization undermines reliance on AIA retainage/approval framework

  - What the declaration relies on: The AIA’s structure to label portions as “mobilization” and imply front-loaded value.

  - Why vulnerable: The owner’s counsel characterizes the governing agreement as an “unsigned proposal contract.” If the AIA terms are disputed or not executed, owner’s reliance on AIA exhibit designations and retainage provisions may not control, increasing factual disputes unsuitable for pre-answer dismissal and weakening the declaration’s conclusory “overpaid” theme.

- No articulation of offsets/backcharges supporting “overpaid” conclusion

  - What the declaration implies: After “crediting the value of the work actually performed,” nothing was due.

  - Why vulnerable: There is no itemization of:

    - Defective/incomplete work valuations,

    - Owner’s completion costs post-termination,

    - Backcharges or setoffs,

    - Liquidated damages, used to reach a zero or negative balance, leaving the “overpaid” assertion unsubstantiated.

- Mechanic’s lien alignment with project chain but not rebutted with contemporaneous architect certifications

  - What the lien shows: Marine identifies JAT as the contracting party; last work 12/4/2025; unpaid $361,080.

  - Why it matters: The owner’s best rebuttal is architect-issued certificates and proof of payment (or denial) through the lien date; those are absent. The G702/G703 reflect only through 9/30, not through 12/16.

### Targeted Cross-Examination/Discovery Angles

- Authenticate and complete the payment record

  - Bank statements showing negotiation of the two 9/4 checks and posting of the 11/3 $60,000 wire (beyond “Needs approval”).

  - Owner/architect certificates and actual payments, including whether the $176,442.66 “current payment due” from the 9/30 pay app was paid or denied.

- Close the 10/1–12/4 earned value gap

  - JAT’s updated G702/G703 through December 2025.

  - Architect site observations and certifications for October–December.

  - Any change orders, backcharges, or termination cost-to-complete analyses used to claim “overpayment.”

- Clarify governing contract status

  - Execution pages for the AIA A101 and A201; if unsigned, identify the operative agreement and its payment/retainage terms.

- Probe basis for “mobilization billed in advance” characterization

  - How mobilization scope and value were defined in Schedule of Values and contract exhibits; whether architect approved 100% mobilization as earned as of 9/30.

- Assess JAT’s “waiver” as litigation-driven

  - Timing, consideration, and purpose of the “waives and relinquishes any present claim” statement; whether it post-dates the lien and serves merely to defeat lien fund rather than reflect the account as of 12/16.

### Bottom Line

- Core weakness: The declaration’s “no lien fund” conclusion rests on a partial, front-loaded snapshot (mobilization plus early payments) and a present-tense waiver—without a full, documented reconciliation of earned vs. paid through the 12/16/2025 lien date. The AIA pay app itself indicates an earned balance due as of 9/30, which is never squarely addressed.